## Gantt Chart
FoodShare – Gantt Chart ¦ 7 Months ¦ 28 Weeks (Jan–Jul 2026)
|  |  |  | Jan '26 |  |  |  | Feb '26 |  |  |  | Mar '26 |  |  |  | Apr '26 |  |  |  | May '26 |  |  |  | Jun '26 |  |  |  | Jul '26
Task / Phase | Owner | Sw | Ew | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
REQUIREMENTS & GATHERING
Requirements Gathering & PRD | Mila, Shuvo | 1 | 2
Feasibility & Scope Definition | Joyeta | 1 | 2
Role Assign | Arin | 2 | 2
SYSTEM DESIGN
System Architecture Design | Shuvo | 3 | 4
Database Schema Design | Mila, Arin | 3 | 4
UI/UX Wireframing | Joyeta | 4 | 5
AUTH MODULE
Signup [All Roles] | Shuvo | 6 | 7
Signin [All Roles] | Mila, Joyeta | 6 | 7
OTP Verification | Arin | 7 | 8
Forgot Password [All Roles] | Shuvo | 8 | 8
Signout [All Roles] | Mila | 8 | 8
DASHBOARD & NAVIGATION
Admin Management Dashboard | Joyeta | 9 | 10
Donor Dashboard | Shuvo | 9 | 10
Volunteer Dashboard | Mila | 10 | 10
Manager Dashboard | Arin | 10 | 10
Top Bar & Bottom Bar | Mila | 10 | 11
PROFILE MODULE
View Profile [All Roles] | Arin | 11 | 12
Edit Profile [All Roles] | Shuvo | 12 | 12
Change Password [All Roles] | Mila | 11 | 12
Change Profile Photo [All Roles] | Joyeta | 12 | 13
FOOD LISTING (DONOR)
Create Food Listing [Donor] | Shuvo | 13 | 14
Edit Food Listing [Donor] | Arin | 14 | 15
Delete Food Listing [Donor] | Shuvo | 15 | 15
View Donation History [Donor] | Joyeta, Mila | 13 | 15
Feedback [Donor] | Arin | 15 | 16
MANAGER FEATURES
View Available Food [Manager] | Mila | 16 | 17
Assign Task [Manager] | Joyeta, Arin | 17 | 18
Track Delivery [Manager] | Shuvo | 17 | 18
View Assigned Task [Manager] | Mila | 18 | 18
VOLUNTEER MODULE
My Task [Volunteer] | Arin | 19 | 20
Delivery Management [Volunteer] | Joyeta | 20 | 21
Rating & Feedback [Volunteer] | Shuvo, Mila | 19 | 21
ADMIN MODULE
User Management [Admin] | Arin | 21 | 22
Verify User [Admin] | Mila | 22 | 22
Reports & Analytics [Admin] | Joyeta, Shuvo | 22 | 23
Add NGO Collaboration [Admin] | Mila | 23 | 24
INTEGRATION & TESTING
Integration & SystemTesting | All 4 | 24 | 25
Bug Fixes & Re-testing | All 4 | 26 | 26
UAT & DEPLOYMENT
User Acceptance Testing (UAT) | All 4 | 27 | 27
Documentation & Deployment | All 4 | 27 | 28

## Resource Schedule
FoodShare – Resource Schedule (7-Month Plan)
|  |  |  | Jan '25 |  |  |  | Feb '25 |  |  |  | Mar '25 |  |  |  | Apr '25 |  |  |  | May '25 |  |  |  | Jun '25 |  |  |  | Jul '25
Member | Role | Focus Areas | PM | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
M1 | Backend / Analyst | Auth, Food Listing, Volunteer, NGO Collab | 7
M2 | Backend / API Dev | Auth, Manager, Delivery API, Reports | 7
M3 | Frontend / UI Dev | Dashboard, Food UI, View Tasks, Admin UI | 7
M4 | Frontend / Test Eng | Profile, Manager UI, Feedback, UAT | 7

## Legend
LEGEND – Phase Color Key
Phase | Weeks | Key Tasks | Team
Phase 0: Req & Planning | W1–W2 | SRS, Scope, Kickoff | All 4
Phase 1: System Design | W3–W5 | Architecture, DB, UI/UX, API | All 4
Phase 2: Auth Module | W6–W8 | Signup, Signin, OTP, Forgot Pwd | M1+M2
Phase 3: Dashboard & Nav | W9–W11 | All role dashboards, Top/Bottom Bar | M3+M4
Phase 4: Profile Module | W11–W13 | View/Edit Profile, Change Pwd/Photo | M1–M4
Phase 5: Food Listing | W13–W16 | Create/Edit/Delete Listing, History | M1+M3
Phase 6: Manager Features | W16–W18 | View Food, Assign Task, Track Delivery | M2+M4
Phase 7: Volunteer Module | W19–W21 | My Task, Delivery Mgmt, Feedback | M1+M2
Phase 8: Admin Module | W21–W24 | User Mgmt, Verify, Reports, NGO | M3+M4
Phase 9: Integration Test | W24–W26 | Integration, Regression, Bug Fix | All 4
Phase 10: UAT & Deploy | W27–W28 | UAT, Documentation, Handover | All 4